| BRIDGEWATER PRIMARY SCHOOL 2018/19 |  |  |  | SCHOOL IMPROVEMENT PLAN |  | AREA: LEADERSHIP & MANAGEMENT |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | School Improvement Overview |  |  |  |  |  |  |  |
| Key priorities for improvement | Responsibility | Date for action/start | Costs |  | Actions |  | Impact (update termly) |  |
| Develop new staff in school and middle leaders | S.L.T. | September 2018 | CPD budget (£5000) & staffing costs |  | - Training for middle leaders and opportunities to practice their skills when leading projects in school. - New staff to be mentored by the DHT & access the NQT programme at Beech Hill Primary. - Performance monitored through appraisal & NQT reports.. |  | Success criteria: More confident and competent staff able to effectively lead their area of the school. Current evidence of impact: |  |
| Continue to develop our work with our partner Trust schools to raise standards and aspirations. | H.T, SLT, Chair of Governors and Heads and Chairs from 7 other schools. | September 2018 | £2000 f or trust Officer. CPD budget |  | - Attend all working parties and board meetings. - Work with colleagues across the Trust to make judgements, share good practice and support with resources and contacts. - Joint training to support our Trust Business Plan and School Improvement Plans. |  | Success Criteria: Raised standards and improved engagement in activities to raise aspirations. Current evidence of impact: |  |
| Embed the ‘In Harmony’ project within Early Years, Y1 & Y2. | H.T, Early Years & KS1 Coordinator & Music Coordinator. SBM | September 2018 | £9000? plus funding from the Arts Council |  | - Work with Sage Gateshead and their Musicians. - Nursery & Reception to have 4x half hour musicality sessions. - Y1& 2 to have two 1 hour taught sessions 2.30 to 3.30 Mon, Wed / Fri learning how to play an instrument. - Work on storage completed. - Look at funding opportunities to continue the project with Sage Gateshead into the future. - Contribute to evaluation tasks. - Begin to perform to a range of audiences. |  | Success Criteria: Children will learn a new skill and be more competent at playing or singing to an audience. This knowledge will transfer to other areas ie. improved concentration, coordination, confidence etc. Current evidence of impact: |  |
| Work with our coach to improve outcomes for our 2 year old children and track their progress to the end of Reception. | HT, Early Years Coordinator, ESM & SEYP. | January 2017 Working with children from Sept 2017 –July 2019 | No cost to school – pilot project with Achievement for All. |  | - Audit completed and continue to work towards actions identified. - Coach to support senior staff in school and track progress - Interventions to be put in place to accelerate progress. - Mentor/coach staff in developing their practice. - Link with other pilot schools and settings to moderate judgements and share practice. |  | Success Criteria: 30 % of children entering Nursery at emerging 30-50months in managing feelings, listening and understanding, 40% in all otherall prime areas. 40% entering Reception emerging 40-60 months. Current evidence of impact: |  |