| BRIDGEWATER PRIMARY SCHOOL 2018-19 |  |  |  |  | SCHOOL IMPROVEMENT PLAN |  | AREA: Outcomes |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | School Improvement Overview |  |  |  |  |  |  |  |
| Key priorities for improvement | Responsibility |  | Date for action/start | Costs |  | Actions |  | Success criteria and evidence of impact (update termly) |  |
| To ensure the percentages of children achieving the national expectation in reading, writing, maths and GPS will at least meet the national expectation In Y2 and Y6. Also the percentage of children achieving the higher national expectation in reading, writing and maths will increase. | S.L.T. Year 2 team and K.S.1 Co-ordinator. Y6 team and KS2 Coordinator. All classes in between |  | September 2018 | £7,000 – CPD & supply |  | - Targets set for all teaching staff to increase the % of children at age related expectation. This will be monitored half termly through lesson observations, work and planning scrutiny, and primarily through pupil progress meetings. - CPD including Bar method, and mastery across the curriculum. - Cross Trust moderation. - Coaching. - Teachers to have the opportunity to observe other teachers. - Use RGS students to support reading. Additional resources and expertise bought in to develop the provision for SEND & EAL children. - Embed our spelling practice and use additional resources to improve spelling across the school. - Use foundation subjects to apply English & Maths skills and knowledge across the curriculum. - Use data & assessment to inform planning and provision, track progress and attainment. - See also Teaching & Learning plan. |  | Success criteria: 84% of children in Y6 will reach the expected standard in R,W & M and children in Y2 will be at or above the national standard 79% R, 77% W, 80% M excludes ARC children . The % at ARE in all other classes will be greater than on entry (see target report). Progress will be above the national average. Current impact: |  |
| To ensure the percentages of children passing the Year 1 and 2 phonics screening check to be in line with the national average. | S.L.T, Early Years, Year 1 and 2 staff, English Coordinator and K.S.1. Co-ordinator |  | September 2018 | £2000 for Debbie Wilson, RWInc coach. |  | - Read, Write Inc training & support and resources to accelerate reading in EYs and KS1. - Differentiated phonics across KS1 & 2. Two phonics sessions daily one at appropriate phase for age and another to meet need. |  | Success Criteria: 88% (excludes ARC) will pass the phonic screen in Y1. 100% (excludes ARC) will pass the phonic screen in Y2. |  |
| Continue to increase the % of children meeting the profile standard in Reception so we are closer to the national average. |  |  |  |  |  | - Additional phonics and reading. - Continue to provide more opportunities to record in maths books. - Introduce more formal teaching where appropriate. |  | Success Criteria: 68%(excluding ARC) will achieve the ELG. |  |